## Lead
Project Name - Employee payroll management
Group Number - 7
Team Lead -Shaik Ashiq Basha(2576345)
Frontend Lead-Shaik Abdulrasheed(2577014)
Backend Lead-Sallappa Gari Sai Kumar(2575473)

## Status Track
Project Status Check Report Team - 7
Sl no. | Employee ID | Name | Domain | Module |  |  | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-16 | 2023-12-17
1 | 2575473 | Sallappa Gari Sai Kumar | Back-end & Frontend | Add/Edit/delete the employees | View Employee |  | ER Diagram ,Database, Division of domain | Backend | Backend | Frontend | Frontend | Testing | PPT & Prparation
2 | 2575952 | Sandeep HN | Back-end & Frontend | Add/Edit/delete Leaves of the employee | View leaves in employee |  | ER Diagram ,Database, Division of domain | Backend | Backend | Frontend | Frontend | Testing | PPT & Prparation
3 | 2576410 | Sapna Kumari | Back-end & Frontend | Create Admin Account | Register into the application | Signout, Home Menu(Nav bars),designing part(Both admin and Employee side) | ER Diagram ,Database, Division of domain | Backend | Backend | Frontend | Frontend | Testing | PPT & Prparation
4 | 2577174 | Saranya R | Back-end & Frontend | Login to portal | Change Password, | Download Salary Slip | ER Diagram ,Database, Division of domain | Backend | Backend | Frontend | Frontend | Testing | PPT & Prparation
5 | 2576987 | Seru Venkata Phani | Back-end & Frontend | Update Profile(Both admin side and Employee side) | View Profile(Both admin side and Employee side) | Home Pages (Both admin side and Employee side) | ER Diagram ,Database, Division of domain | Backend | Backend | Frontend | Frontend | Testing | PPT & Prparation
6 | 2577014 | Shaik Abdulrasheed | Back-end & Frontend | Add/Edit/Delete the Salary of the employee | View Salary,View Salary Slips |  | ER Diagram ,Database, Division of domain | Backend | Backend | Frontend | Frontend | Testing | PPT & Prparation
7 | 2576345 | Shaik Ashiq Basha | Back-end & Frontend | Add/Edit/delete mark the attendance of employees | View his/her attendance. |  | ER Diagram ,Database, Division of domain | Backend | Backend | Frontend | Frontend | Testing | PPT & Prparation
8 | 2576579 | Shaik Najeemm | Back-end & Frontend | Add/Edit/delete the schedule the work of the employees | View his/her schedule set by Admin. |  | ER Diagram ,Database, Division of domain | Backend | Backend | Frontend | Frontend | Testing | PPT & Prparation

## Status Meeting
Status Meeting Group - Name
Meeting Date | Time | Progress Check | Time | Problem Solving
2023-12-11 | 11:30 | a | 14:00 | a
2023-12-12 | 9:30 | a | 16:00 | a
2023-12-13 | 10:00 | a | 18:30 | a
2023-12-14 | 10:00 | a | 16:00 | a
2023-12-15 | 10:00 | a | 16:00 | a
2023-12-16 | 0.41667 | a | 0.66667 | a
2023-12-17 | 0.41667 | a | 0.66667 | a